## Tabelle1
Risk Name | Risk Description | Risk Probability of Occurrence(0-10) | Risk Impact(0-10) | Risk Factor | Risk Mitigation | Person in Charge of Tracking
Bad Time Management | Not enough time to finish the project. Underestimate the time required to implement it. Can't meet the deadline. | 2 | 10 | 20 | Work in Overtime, time management | Jonas S.
Underestimating Tasks | We don't have a lot of experience with web development. This could lead to us trying to implement features that take up way to much time. | 10 | 5 | 50 | Git Gud | Jonas A.
Requirement Change | Requirements could change during development | 3 | 6 | 18 | Work in Overtime | Moritz
Non-Commercial Use Licence | Since we want to use our project commercially, some tools that we may want to use may not be available for free. | 7 | 2 | 14 | Read the licence agreement of all tools that we want to use | Jonas A.
Reprogramming | Something doesnt work out as planned and big software parts need to be reprogrammed. | 3 | 9 | 27 | Clever planning | David
Django | Django may not allow us to do everything we want to do, restricting the feature set of our project or forcing us to switch frameworks. | 3 | 8 | 24 | Inform ourselves more about the capabilities of Django | David
Loss of All Data | When storing all data to a single device, a loss of all data could be possible | 1 | 10 | 10 | Use GIT religiously | Jonas A.